## Sheet1
|  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
Milestone | Days | Who | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8
General
Test Plan Template Creation | 1d | J | bar: January 28 to February 4
Test Plan Document | 30d | J/D/S | bar: February 11 to March 18
Phase 3 Deliverables |  | J | bar: March 25
Testing
Testing & QA | 8d | D/S | bar: March 11 to March 25
Implementation
Code | 45d | T
Build 1 | 20d | T | bar: January 7 to January 28
Build 2 | 20d | A | bar: February 18 to March 18
Build 3 | 15d | A | bar: March 25 to April 8
Notes: J (Jenny), D (Danny), S (Siming), T (Tony), A (Amar)